## Stories
Rank | Story | Status
1 | Save data to database | C
2 | Create new Auction | C
3 | Edit existing Auction | C
4 | Open Auction | C
5 | Create new Donor | C
6 | Edit existing Donor | C
7 | Create new Item | C
8 | Edit existing Item | C
9 | Main Form save window settings | C
10 | Edit Auctions Form save window settings | C
11 | Edit Donors Form save window settings | C
12 | Items Grid save column settings | C
13 | Auctions Grid save column settings | C
14 | Donors Grid save column settings | C
15 | Document Editor - save window settings | C
16 | Copy Donors from one Auction to another | C
17 | Show all Items by Donor regardless of Auction | C
18 | Document Editor - Request Letter | C
19 | Document Editor - Follow Up Letter | C
20 | Print Donor Letters | C
21 | Show all Items by Donor save window settings | C
22 | About Form | C
23 | Donors to Print Letter for | C
24 | Send Email to Donors | D
25 | Print Address Labels | D
26 | Who has not yet responded Report | C
27 | Import Items from Excel | N
28 | Export to Excel | N
29 | Splash Screen | N
30 | EULA | N
31 | Print Item Labels | N
32 | Print Bid Sheets | N
33 | Attach/Print external document | N
34 | Print Items Grid | N
35 | Import Form Letters | N
| Store Image of Item | N

## Tasks
Delete Image once added?